## BOM
Open Duck Mini v2 — India-sourced BOM (for 10 Oct 2026 event)
Prices in INR incl. GST where the vendor shows it. 'Verified' = checked on vendor page 25 Sep 2026; 'Est.' = typical Indian retail price, confirm at checkout. Blue = editable inputs; yellow columns = fill in as you order.
Reference BOM (EUR): github.com/apirrone/Open_Duck_Mini → README → BOM Google Sheet. Upstream total ≈ €398 base / €432 with expression pack.
# | Priority | Part | Exact spec / variant to buy | Qty | Spares | Unit ₹ | Line ₹ | Vendor | Link | Stock / dispatch | Price | Notes | Ordered? | ETA
SERVOS & CONTROL
1 | P0 | Feetech STS3215 serial bus servo | STS3215-C001 — 7.4 V, 19.5 kg·cm, 1:345 gear. NOT the 12 V/30 kg (C018) or 1:147 (C046) variants | 14 | 2 | 2224.3 | 35588.8 | Evelta | https://evelta.com/sts3215-7-4v-19kg-dual-axis-ttl-string-servo-motor/ | 80 in stock; ships 24 h from Mumbai | Verified | Sim-to-real motor model (BAM) is identified for the 7.4 V C001. 2 spares = cheap insurance for a live demo.
2 | P0 | Waveshare Bus Servo Adapter (A) | UART/USB-C bus servo driver for ST/SC servos | 1 | 1 | 789 | 1578 | REES52 | https://rees52.com/products/waveshare-serial-bus-servo-driver-board-all-in-one-servo-driver-board-with-integrated-power-control-for-st-sc-actuators-rs8478 | 23 in stock; express 2–3 working days | Verified | Robocraze listing sold out. Upstream runs it off 2S (7.4 V).
3 | P0 | Raspberry Pi Zero 2 W | Official board (solder a 40-pin header, or buy the WH variant) | 1 | 0 | 1748.76 | 1748.76 | Evelta | https://evelta.com/raspberry-pi-zero-2-w/ | In stock; ships 24 h | Verified | Robocraze out of stock; Robu listed ₹2,079 as backup.
4 | P0 | 40-pin male GPIO header | 2×20, 2.54 mm | 1 | 1 | 30 | 60 | Robu / Evelta |  | Stock item | Est. | Skip if you buy the Zero 2 WH.
5 | P0 | microSD card | 32 GB, A1/U1 (SanDisk Ultra or similar) | 1 | 1 | 450 | 900 | Amazon.in |  | 1–2 days | Est. | Flash the prebuilt Duck image (runtime repo → Releases).
6 | P0 | IMU — Adafruit BNO055 breakout | Adafruit #2472 (the runtime uses the adafruit_bno055 library over I2C) | 1 | 0 | 4191.58 | 4191.58 | Fab.to.Lab | https://www.fabtolab.com/adafruit-9-dof-absolute-orientation-imu-fusion-breakout-bno055 | In stock | Verified | Robu has it at ₹4,619. Clone GY-BNO055 boards are cheaper but riskier on Pi I2C. Keep the genuine one for the deadline.
7 | P0 | Foot contact switches | Omron SS-5GL / SS-10 body micro switch | 4 | 2 | 60 | 360 | Robu | https://robu.in/product/3d-printer-limit-switch-endstop-omron-ss-5gl/ | Stock item | Est. | Press-fit into feet; wired to Pi GPIO 22/27.
8 | P1 | 9 g micro servos (antennas) | SG90 or MG90S | 2 | 1 | 120 | 360 | Robu / Robocraze |  | Stock item | Est. | Expression only; PWM from Pi GPIO 12/13.
POWER
9 | P0 | 18650 Li-ion cells | Samsung INR18650-30Q 3000 mAh, high drain (upstream uses Molicel P30B) | 2 | 2 | 609 | 2436 | Robu | https://robu.in/product/samsung-18650-30q-li-ion-battery/ | Stock item | Verified | Buy genuine high-drain cells only. The 2 spares make a second pack for event day.
10 | P0 | 2S 18650 cell holder | 2-cell series holder with leads | 1 | 1 | 60 | 120 | Robu |  | Stock item | Est.
11 | P0 | 2S BMS 20 A with balance | 7.4–8.4 V protection board | 1 | 1 | 250 | 500 | Robu | https://robu.in/product/2s-20a-18650-lithium-battery-protection-board/ | Stock item | Est. | Upgraded from the 10 A board (₹72) for headroom at servo current peaks.
12 | P0 | UBEC 5 V / 3 A | 2–6S input, 5 V out, powers the Pi | 1 | 0 | 269 | 269 | Robu | https://robu.in/product/ubec-5v-3a/ | Stock item | Verified
13 | P0 | USB-C 2S charger module | IP2326-based 5 V→8.4 V, balance | 1 | 0 | 250 | 250 | Robu / Amazon.in |  | Stock item | Est. | Or charge cells in a standalone 18650 charger.
14 | P0 | Power switch | Mini rocker / slide, ≥10 A DC | 1 | 1 | 50 | 100 | Robu |  | Stock item | Est.
15 | P0 | XT30 connector pairs | Male + female | 3 | 0 | 50 | 150 | Robu |  | Stock item | Est.
16 | P0 | DC 2.1 mm barrel jack pigtails | Male, 5.5×2.1 mm, to feed the servo adapter | 2 | 0 | 30 | 60 | Robu |  | Stock item | Est.
17 | P1 | Standalone 18650 charger | 2-bay smart charger (e.g., LiitoKala Lii-202) | 1 | 0 | 900 | 900 | Amazon.in |  | 1–2 days | Est. | Charges the spare pack while the robot is running.
MECHANICAL & CONSUMABLES
18 | P0 | Ball bearings | 608ZZ (8×22×7 mm) | 3 | 2 | 30 | 150 | Robu / local |  | Stock item | Est.
19 | P0 | M3 brass heat-set inserts | M3 × ~5 mm OD knurled, 100 pcs | 1 | 0 | 450 | 450 | Robu |  | Stock item | Est. | Upstream doesn't give a count; 100 is plenty.
20 | P0 | M3 screw kit | Hex socket, M3×6/8/10/12/16, stainless, ~300 pcs | 1 | 0 | 600 | 600 | Amazon.in |  | 1–2 days | Est. | The plastic servo-mount screws come with the servos.
21 | P0 | PLA filament | 1.75 mm, 1 kg (eSUN / Numakers) | 2 | 0 | 1000 | 2000 | Amazon.in / Robu |  | 1–2 days | Est. | All parts 15% infill. About 1 kg in use; 2 kg covers reprints.
22 | P0 | TPU 95A filament | 1.75 mm, 500 g–1 kg | 1 | 0 | 1500 | 1500 | Zee3D / 3Idea / Amazon.in | https://www.zee3d.in/product-page/artillery-premium-black-95a-flexible-tpu-filament-1-kg-1-75-mm | Stock item | Est. | Only for foot_bottom_tpu ×2 at 40% infill.
23 | P0 | Loctite 243 (blue) | Medium threadlocker, 10 ml | 1 | 0 | 450 | 450 | Amazon.in |  | 1–2 days | Est. | Use on every metal-to-metal screw. Walking vibration loosens them.
24 | P0 | Cables | Micro-USB→USB-C 15 cm (Pi→servo board) + micro-USB 50 cm | 2 | 0 | 200 | 400 | Amazon.in |  | 1–2 days | Est. | Must be data cables (OTG).
25 | P0 | Silicone wire + heat shrink | 18 AWG and 24 AWG red/black, heat-shrink assortment | 1 | 0 | 450 | 450 | Robu |  | Stock item | Est.
26 | P1 | Braided cable sleeve | 6–8 mm | 1 | 0 | 200 | 200 | Amazon.in |  | 1–2 days | Est.
27 | P1 | Spare servo cables | 3-pin 5264 bus cables, 15–20 cm | 4 | 0 | 60 | 240 | Evelta / Robu |  | Stock item | Est. | The cables supplied with the servos may be short for some runs.
EXPRESSION PACK (optional, adds demo appeal)
28 | P2 | Camera for Pi Zero | OV5647 mini + Zero CSI ribbon | 1 | 0 | 650 | 650 | Robu / Robocraze |  | Stock item | Est.
29 | P2 | I2S amplifier | MAX98357A breakout | 1 | 0 | 300 | 300 | Robu |  | Stock item | Est.
30 | P2 | Speaker | 3 W 4 Ω, ~28–40 mm | 1 | 0 | 120 | 120 | Robu |  | Stock item | Est.
31 | P2 | USB mini microphone | Plug-in USB mic | 1 | 0 | 350 | 350 | Amazon.in |  | 1–2 days | Est.
32 | P2 | LEDs + diffusers + reflector | 3× 5 mm LEDs (eyes + projector) | 1 | 0 | 150 | 150 | Robu |  | Stock item | Est.
CONTROL INPUT
33 | P1 | Gamepad | Xbox Wireless Controller (Bluetooth). The runtime is written for it | 1 | 0 | 5000 | 5000 | Amazon.in | https://www.amazon.in/xbox-controller/s?k=xbox+controller | 1–2 days | Est. | Skip if the team already has one.
|  | Core build (P0) |  |  |  |  | 54312.14
|  | Recommended extras (P1) |  |  |  |  | 6700
|  | Expression pack (P2) |  |  |  |  | 1570
|  | Grand total (all) |  |  |  |  | 62582.14
|  | Spares included in the totals |  |  |  |  | 7595.6
|  | Shipping allowance (4–5 vendors) |  |  |  |  | 2000
|  | All-in estimate |  |  |  |  | 64582.14
Legend: P0 = must have to walk · P1 = strongly recommended for a live demo · P2 = optional 'expression' features. Edit the blue Qty/Spares/Unit cells and the totals update. Mark Ordered? Y/N and ETA as you go.
Assumes in-house FDM printer(s), soldering station with a heat-set insert tip, hex drivers and a laptop, so none of these are costed. Outsourced printing ≈ ₹6–10k extra plus turnaround risk.

## Timeline
Build plan: order 25 Sep, demo 10 Oct (15 days)
Date | Day | Workstream | Task | Gate / done when | Owner | Status
25 Sep | Fri | Procurement | Order everything today: Evelta (servos, Pi), REES52 (servo board), Fab.to.Lab (IMU), Robu (power, switches, inserts), Amazon.in (filament, screws, Loctite, cables) | All orders confirmed
25–30 Sep | Fri–Wed | Printing | Start printing /print STLs tonight: legs + trunk first, then head/body. PLA 15% infill; TPU feet 40% | All parts printed. Allow ~50–70 printer-hours; split across 2 printers
26–28 Sep | Sat–Mon | Software | Flash the prebuilt Duck image (runtime repo v2, Releases). Set up Wi-Fi/SSH. Pull BEST_WALK_ONNX_2.onnx. Optional: run Open_Duck_Playground in MuJoCo on a PC | Pi boots headless on SSH
29 Sep–1 Oct | Tue–Thu | Receiving | Deliveries land. Chase anything not shipped by 29 Sep. 2 Oct is Gandhi Jayanti, a courier holiday | Everything on the bench by 1 Oct
30 Sep–1 Oct | Wed–Thu | Servos | configure_motor.py per servo (IDs 10–14, 20–24, 30–33). Fit horns at zero. Label every servo | 14 servos ID'd + labelled
1 Oct | Thu | Power | Build the 2S pack: match cell voltages, BMS, switch, XT30, UBEC. Check 5 V at the Pi and ~8 V at the servo board | Pack powers the Pi + board with no sag
2–4 Oct | Fri–Sun | Assembly | Heat-set inserts → feet → shins → thighs → hips → trunk → neck/head → body. Loctite on metal-to-metal screws. Follow docs/assembly_guide.md + Onshape CAD | Full mechanical assembly
4–5 Oct | Sun–Mon | Bring-up | Wiring (IMU, foot switches, servo bus). raw_imu.py, check_motors.py, find_soft_offsets.py → duck_config.json | All joints respond; IMU frame correct
6–7 Oct | Tue–Wed | Walking | Run v2_rl_walk_mujoco.py with BEST_WALK_ONNX_2 + Xbox pad. Tune offsets and IMU orientation. Test on the event floor type | Walks 2+ min, turns, recovers
8 Oct | Thu | Hardening | Re-torque screws, battery endurance test, charge the spare pack, pack a spares kit (servos, board, cells, SD image) | 30-min demo loop is stable
9 Oct | Fri | Buffer | Slack for a failed servo, reprint or rework. Demo rehearsal | Go / no-go
10 Oct | Sat | Event | Demo | —

## Option comparison
Candidate comparison (as of 25 Sep 2026)
| Open Duck Mini v2 (recommended) | Bimo (mekion) | Microduck (Pollen / HF)
Size / weight | ~42 cm | 45 cm / 1.6 kg | 25 cm / 0.8 kg
DOF / actuators | 14× STS3215 (+2 SG90 antennas) | 8× STS3215 | 15× Dynamixel XL330
Compute | Pi Zero 2 W | Custom RP2040 PCB (+ optional SBC / PC) | Radxa Zero 3W + custom imu_to_dxl board
CAD / STLs public? | Yes: STLs in repo + Onshape | No: 'coming soon' | No: hardware is proprietary. Community replica is unverified
Custom PCB needed? | No (off-the-shelf boards) | Yes (RP2040 board, not published) | Yes (IMU→DXL board)
Kit purchase | n/a | $500, EU/US only, ships 'early Q4 2026' | $399 preorder
Walking policy available | Yes: BEST_WALK_ONNX_2 + prebuilt Pi image | CPG gait + Isaac Lab | Yes (MuJoCo/PPO), but needs the hardware
India sourcing | All parts stocked in India | Servos yes; PCB/CAD no | XL330 import; PCB fab ~1–2 wks
Hits 10 Oct? | Yes, with ~2 days buffer | No | No